## TIPS Publication List
Problem ID*+ | Originating Service | Issue Description (BOD) | Impacted Module | Expected PROD Delivery Date
Production Problems Impacting TIPS
PBI000000222250 |  | AM05 error code is part of TIPS.stat.M9 statistical indicator (Number of national unsettled IP transactions in non-Euro currency grouped by reason code) and should capture a duplicate transaction received by TIPS from the operational database; unfortunately this also means that there's "no room", on the operational database, to store the second (duplicated) transaction without overwriting the first one, that is already in a final state. The above implies that the statistical indicator for AM05 would always appear as 0 even when transactions have been rejected due to a failed Duplication check. Customer agreed to remove such indicator from Additional Statistics, nevertheless solutions to extract the indicator in alternative ways are under analysis. | TIPS Queries | 2025-06-19
PBI000000233844 |  | 1. Business Scenario Description: Query performed via TIPS GUI in Advanced Payment Transaction search/list screen – Payment Details 2. Issue Description: For expired transactions both ‘Settlement Timestamp’ and ‘Settlement Business Date’ fields are filled in instead of being empty. TIPS GUI behavior is not in line with TIPS UHB description for the involved fields (i.e. expected to be empty if a transaction is not settled). 3. Workaround: No workaround 4. TARGET Services concerned: TIPS 5. Effects and restrictions on concerned TARGET Service: Values shown on TIPS GUI for both ‘Settlement Timestamp’ and ‘Settlement Business Date’ fields should be ignored 6. Required SW change: A fix in the software is needed to correctly manage the values shown in the TIPS GUI | TIPS GUI | 2025-06-19
PBI000000234349 |  | 1. Business Scenario Description: The FItoFICustomerCreditTransfer message allows instructing TIPS for an Instant Payment transaction of a positive amount of money from the originator participant account to the beneficiary participant account. Message specification is compliant to EPC DS-02 Inter-PSP Payment Dataset as described in the SEPA Instant Credit Transfer scheme Rulebook. 2. Issue Description: In TIPS XSD customization, pacs.008 FIToFICstmrCdtTrf/CdtTrfTxInf/RmtInf/Strd/CdtrRefInf/Tp and FIToFICstmrCdtTrf/CdtTrfTxInf/RmtInf/Strd/CdtrRefInf/Ref XML tags are defined as optional fields. As per the SEPA Instant Credit Transfer Inter-PSP IGs 2023 Version 1.2, both message element have a SEPA multiplicity equals to [1..1] but a [0..1] multiplicity in TIPS-customized MyStandards XSDs. 3. Workaround: no workaround needed, both fields can be used without restrictions but they are not mandatory. 4. TARGET Services concerned: TIPS. 5. Effects and restrictions on concerned TARGET Service: no effects on TIPS, both fields can be used without restrictions. Moreover the TIPS usage for these fields is restricted to a pure schema validation. 6. Required SW change: Align the pacs.008 XSD scheme (both highlighted tags) with the next release of EPC SCTInst IGs, with an entry-into-force date foreseen, at the moment, for October 2025. 7. CRDM object: n/a. 8. DWH report: n/a. | TIPS-A2A | 05/10/2025
PBI000000234532 |  | 1. Business Scenario Description: The ResolutionOfInvestigation message is sent by the Assignee party of a Recall, triggered by an Assigner party for a formerly settled Instant Payment transaction, as a negative response. Additionally, the ResolutionOfInvestigation message can be sent in reply to a Request for Status Update on a Recall. Message specification is compliant to EPC DS-06 Inter-PSP Payment Dataset as described in the SEPA Instant Credit Transfer scheme Rulebook. 2. Issue Description: In TIPS XSD customization, camt.029 RsltnOfInvstgtn/CxlDtls/TxInfAndSts/CxlStsRsnInf/Rsn XML tag is defined as optional field. As per the SEPA Instant Credit Transfer Inter-PSP IGs 2023 Version 1.2, this message element have a SEPA multiplicity equals to [1..1] but a [0..1] multiplicity in TIPS-customized MyStandards XSDs. 3. Workaround: no workaround needed, the field can be used without restrictions but it is not mandatory. 4. TARGET Services concerned: TIPS. 5. Effects and restrictions on concerned TARGET Service: no effects on TIPS, the field can be used without restrictions. Moreover the TIPS usage for this field is restricted to a pure schema validation. 6. Required SW change: Align the camt.029 XSD schema with the next release of EPC SCTInst IGs, with an entry-into-force date foreseen, at the moment, for October 2025. 7. CRDM object: n/a. 8. DWH report: n/a. | TIPS-A2A | 05/10/2025
PBI000000234674 |  | 1. Business Scenario Description: The FItoFIPaymentStatusReport message is used in 12 different business cases applied to a wide range of TIPS functionalities. Message specification is compliant to EPC DS-03 Confirmation Message as described in the SEPA Instant Credit Transfer scheme Rulebook. 2. Issue Description: In TIPS XSD customization, pacs.002 FIToFIPmtStsRpt/TxInfAndSts/OrgnlTxRef/PmtTpInf XML tag is defined as optional field. As per the SEPA Instant Credit Transfer Inter-PSP IGs 2023 Version 1.2, this message element have a SEPA multiplicity equals to [1..1] but a [0..1] multiplicity in TIPS-customized MyStandards XSDs. 3. Workaround: no workaround needed, the field can be used without restrictions but it is not mandatory. 4. TARGET Services concerned: TIPS. 5. Effects and restrictions on concerned TARGET Service: no effects on TIPS, the field can be used without restrictions. Moreover the TIPS usage for this field is restricted to a pure schema validation. 6. Required SW change: Align the pacs.002 XSD schema with the next release of EPC SCTInst IGs, with an entry-into-force date foreseen, at the moment, for October 2025. 7. CRDM object: n/a. 8. DWH report: n/a. | TIPS-A2A | 05/10/2025
PBI000000233509 |  | 1. Business Scenario Description: Routing object. Creation of conditional routing for the delivery of the TIPS Directory 2. Issue Description: In routing new/edit screen the message type reda.xxx used for the delivery of TIPS Directory is not selectable in the list of available æMessage TypesÆ when a TIPSCRDM network service is selected. reda.xxx value is still mapped under TIPS network services according to the previous setup when the delivery of TIPS Directory was directly performed via TIPS and not via CRDM. 3. Workaround: No workaround available. 4. TARGET Services concerned: TIPS 5. Effects and restrictions on concerned TARGET Service: Conditional routing is currently not available for TIPS Directory. Default routing need to be used. 6. Required SW change: A change of the software is needed to manage the selection of reda.xxx from the list of available æMessage TypesÆ when a TIPSCRDM network service is selected 7. CRDM object: Routing | CRDM | 22/11/2025
PBI000000234172 |  | 1. Business Scenario Description: the TIPS pricing policy introduced with CR TIPS 0057 foresees new service items to charge TIPS participants' ownership of accounts and AAUs (3009 for TIPS DCA, 3010 for TIPS ASTA, 3011 for AAUs defined on TIPS DCA and 3012 for AAUs defined on TIPS ASTA). These service items must be charged to a participant in a givin billing period only if the related account/AAU has been opened at least for one business date during the billing period, so no charges must be applied for accounts/AAUs with future validity dates. 2. Issue Description: 3012 service items related to AAUs with opening date equal to the first business date of the subsequent billing period BPx+1 are wrongly charged in the current billing period BPx (e.g. an AAU with valid from 2024-11-01 is charged to its owner in the billing period 2024-10-01 - 2024-10-31). 3. Workaround: wrongly charged amounts calculated from the system can be rebalanced by adding Credit Manual correction to relevant invoice data. 4. TARGET Services concerned: TIPS 5. Effects and restrictions on concerned TARGET Service: TIPS participants are wrongly charged for AAUs defined on TIPS ASTA even they have not been opened during the billing period. 6. Required SW change: BILL CoCo component in charge of accounts/AAUs data gathering must be fixed. 7. CRDM object: na 8. DWH report: na | BILL | 15/02/2025
PBI000000234565 |  | 1. Business Scenario Description: Service item 3009 foreseen in TIPS Pricing Policy must be applied to any TIPS DCA which has been active for at least one business day during the billing period (i.e. for which the "Opening Date" fell before or during the billing period, and for which the "Closing Date" falls during or after the billing period). 2. Issue Description: A TIPS DCA is created with an Opening Date in the future setting a value within the current billing period (i.e. Billing period 2024-09-01 to 2024-09-30 û Opening Date 2024-09-13). Following that, before reaching the Opening Date of the TIPS DCA, the Opening Date is changed and set to a future value out of the current billing period (i.e. new value of the Opening Date: 2024-10-07). In this scenario no charges should be applied to TIPS DCA holding party because the TIPS DCA has never been open during the interested billing period. Due to a software issue, BILL wrongly charges to its holding party also TIPS DCAs covering this scenario in the invoice of the billing period 2024-09-01 to 2024-09-30. 3. Workaround: Wrongly charged amount can be realigned by adding a credit manual correction to invoice data. 4. TARGET Services concerned: TIPS 5. Effects and restrictions on concerned TARGET Service: Participants are overcharged for TIPS DCA covering scenario described in point 2). 6. Required SW change: The processing concerning the opening date of TIPS DCA must be fixed. 7. CRDM object: na 8. DWH report: na | BILL | 15/02/2025
Problem ID*+ | Originating Service | Issue Description (BOD) | Impacted Module | Expected PROD Delivery Date
Production Problems Impacting Common Components (CoCo's)
PBI000000233438 | TIPS | 1. Business Scenario Description: The operating modules record the consumption made by the participants on the TARGET services, aggregate them on a daily basis by service item, party to be charged and responsible party and produce the Daily Aggregated Consumption Data. These are sent to BILL which enriches and validates them with CRDM configurations. Then BILL aggregates Daily Aggregated Consumption Data by the period to which the invoice will refer and by responsible party and then produces the Aggregated Consumption Data. Starting form Aggregated Consumption Data for a system entity, then BILL calculates the price to apply based on the configuration of Service Items and produces the Invoice Data. 2. Issue Description: Due to the absence of a valid price in a time interval for Service Item already configured in CRDM, BILL abends for an entire community/Service. The invoice data generetion process is stopped. In this case, new service items should have started to be included into invoices from July 2024 setting Valid From of them to 01/07/2024 in CRDM. But these new service items started to be included in the billing calculation in June 2024. Since their validity started from July, instead of skipping them (not valid in June), invoice data generation process was stuck. 3. Workaround: Configure Service Items with valid price for the relevant Billing Period 4. TARGET Services concerned: All Services are involved 5. Effects and restrictions on concerned TARGET Service: Billing process is stuck and no Invoice Data or PDf invoices are generated 6. Required SW change: A fix should be put in place to prevent BILL from going abend for an entire community/Service due to the absence of a valid price in a time interval for a service item already configured in CRDM. 7. CRDM object: 8. DWH report: | BILL | 2025-06-14
PBI000000233483 | TIPS | 1. Business Scenario Description: Into the Invoice, the invoice issuer can insert debit or credit items in addition to the ones relative to TARGET services consumption, this information is stored by Manual Correction entity. These additional items can refer to an already registered Service Item or to a custom one. It is possible to add Manual Correction also when the Participant has no consumption 2. Issue Description: In case the participant has no consumption, adds a Manual Correction and then deletes it, it is not possible to insert any other manual correction for the same participant, billing period and service. 3. Workaround: no workaround 4. TARGET Services concerned: all services are involved 5. Effects and restrictions on concerned TARGET Service: when the problem occurs it is not possible to insert any other manual correction for the same receiving party, billing period and service. 6. Required SW change: A software fix should be implemented to allow Manual correction to be inserted for a participant with no consumption and on which a Manual correctio has been already inserted and deleted. 7. CRDM object: na 8. DWH report: na | BILL | 2025-06-14
PBI000000233493 | TIPS | 1. Business Scenario Description: Before the creation of the invoices, the invoice data can be complemented with additional service items inserted as manual corrections for both CBs and CB Participants. In case a party did not perform consumption during the billing period, it is still possible to add manual correction, this result in the creation of an invoice dataset containing only the manual correction which will be reflected in the related invoice. 2. Issue Description: When a manual correction is added for a party without consumption BILL creates the related invoice data set, if the party BIC code is associated in CRDM also to other parties in different validity periods, BILL creates invoice dataset containing the same manual correction also for these parties despite the validity period of their BIC code. This results in multiple rows displayed in Invoice Data List screen for the same manual correction. 3. Workaround: The manual correction is correctly added so for the user performing the operation no workaround is needed. Instead an LLI is needed to ignore invoice dataset created for other parties. 4. TARGET Services concerned: TIPS, T2, T2S (Only CB users). Please note that the scenario is very uncommon considering its preconditions (BIC code used by different parties in different validity periods and manual correction added to a party without consumption). 5. Effects and restrictions on concerned TARGET Service: Multiple rows displayed in Invoice Data List screen for the same manual correction. 6. Required SW change: BILL must take into account the validity period of the party BIC in the creation of manual correction for a party without consumption avoiding multiple occurrences. 7. CRDM object: na 8. DWH report: na | BILL | 2025-06-14
PBI000000233501 | TIPS | 1. Business Scenario Description: A community (NCB + Participants) can perform consumption in different currencies (e.g. EUR and non-EUR currency). In CRDM configuration, this result in different system entityes having the same country code but different currencies. Consumptions performed by community must be processed properly by billing process both for EUR and non-EUR currency (via CR CSLD 0088 changes). 2. Issue Description: If a community perform consumption in different currencies (different system entities with same country code but different currencies), the billing process gets stuck for both system entities. 3. Workaround: LLI performed by 4CB, no workaround via application. 4. TARGET Services concerned: TIPS, T2, T2S 5. Effects and restrictions on concerned TARGET Service: Billing process gets stuck for both system entities in which community perform consumption. 6. Required SW change: BILL must be able to manage consumption of the same community in different currencies. 7. CRDM object: na 8. DWH report: na | BILL | 2025-06-14
PBI000000234035 | TIPS | 1. Business Scenario Description: As per the TIPS CR0066, It is requested that BILL is able to process and display unit prices with 5 decimals. This implies: (i) the possibility to capture the unit price in CRDM with at maximum 5 decimal positions (ii) the usage of the unit price (at maximum 5 decimal positions) in any relevant BILL automated process, BILL screens, and A2A/U2A invoices/queries. 2. Issue Description: The customer is trying to insert a Manual Correction setting a unit price with 5 decimal digit but on the screen the error ôUnit price is invalidö is displayed and it is not possible to insert the manual correction since the button Submit is not enabled. 3. Workaround: No workaround. 4. TARGET Services concerned: T2, T2S, ECMS. Since the usage of the unit price (at maximum 5 decimal positions) in any relevant BILL automated process, BILL screens, and A2A/U2A invoices/queries is foreseen and the Manual Correction can be added for any Target Service, all Services are involved 5. Effects and restrictions on concerned TARGET Service: It is not possible to insert Manual Correction with 5 decimal position, and in particular it is not possible to manage the ACH fee for band 4 with its unit price set at EUR 0.00015 6. Required SW change: a software fix should be put in place in order to allow the insertion of prices with 5 decimal position for the Manual Corrections 7. CRDM object: n/a 8. DWH report: n/a | BILL | 2025-06-14
PBI000000233525 | TIPS | 1. Business Scenario Description: Creation of Authorized Account User object using a BIC that is not existing in the BIC Directory 2. Issue Description: In the business rule DCC2003 "The BIC pattern, unless it contains a wildcard, must refer to an existing and active BIC", the check on the existence of the inserted BIC is not correctly executed in the software because it is only executed in case of inserted AAU Valid From greater than the current business date, instead of equal or greater than current business date. 3. Workaround: No workaround available. 4. TARGET Services concerned: TIPS and T2 5. Effects and restrictions on concerned TARGET Service: Under the described scenario and conditions (i.e. Creation of AAU object with Valid From equal to the current business date and referencing a BIC that is not existing in the BIC Directory), the AAU will be created but the inconsistent setup could not be used by the respective TARGET service since it will not be possible to complete the CRDM configuration and create the related æDN-BIC RoutingÆ object (i.e. the check on BIC existence in BIC Directory will be performed by business rule DRC8003). 6. Required SW change: A change in the software is needed to correctly perform the check for business rule DCC2003 also when the inserted AAU Valid From date is equal to the current business date 7. CRDM object: Authorized Account User | CRDM | 2025-11-22
PBI000000233821 | TIPS | 1. Business Scenario Description: BILL sends a camt.077 CONS message containing Aggregated Consumption Data after their generation to NCBs having consumption message feature active in invoice configuration and proper message subscription / routing configuration. This feature is designed for NCBs that do not activate direct invoicing but manage billing to their participants themselves and therefore need a view of the consumption made by their participants. 2. Issue Description: BILL-A2A wrongly reports service items related to account (ACMS and SETT) in camt.077 CONS message. Indeed, BILL-A2A reports tags related to these service items multiple times using a random choosen account. 3. Workaround: No workaround. 4. TARGET Services concerned: TIPS, T2, T2S (Only CB users). Please note that only CBs opting for Consumption Message sending feature are impacted (Consumption Message flag = true in Invoice Configuration). 5. Effects and restrictions on concerned TARGET Service: CB users opting for Consumption Message sending feature can't use camt.077 CONS to reconcile their participants' consumption internally. 6. Required SW change: BILL-A2A component must report properly service item related to accounts, it must report the correct number of tags with correct account number. 7. CRDM object: na 8. DWH report: na | BILL | 2025-02-15
PBI000000233846 | TIPS | 1. Business Scenario Description: BILL A2A Query CUMU which allows duly authorized users to retrieve invoice data aggregated in a cumulative way; the query flow involves a camt.076 CUMU request and a camt.077 CUMU response. In the camt.077 CUMU response the rounding to the 2nd decimal digit foreseen by BILL UDFS for visualization phase must be applyed. According to BILLING documentation: "The rounding to the 2nd decimal digit foreseen by EUR is performed only during the visualization phase (PDF, Screen, camt.077). All data used during each step of the computation is based on the precision to the 5th decimal place (the 6th decimal is rounded by defect (0-4) or by excess (5-9)). The rounding to the 2nd decimal digit foreseen by EUR is performed only during the visualization phase (PDF, Screen, camt.077)." 2. Issue Description: The value of tag TotalInvoiceAmount (Document/BllgRpt/BllgRptOrErr/BllgRpt/InvcTtls/TtlInvcAmt) in camt.077 CUMU is truncated to the 2nd decimal digits instead of being approximated as foreseen by BILLING UDFS resulting different from the value of "Grand Total" field in PDF. 3. Workaround: Correct value of TtlInvcAmt can be retrieved either via U2A in the PDF Invoice and via A2A in camt.077 INVC. 4. TARGET Services concerned: TIPS, T2S, T2 5. Effects and restrictions on concerned TARGET Service: Customers using A2A CUMU Query will have a wrong value of tag Document/BllgRpt/BllgRptOrErr/BllgRpt/InvcTtls/TtlInvcAmt. 6. Required SW change: BILL A2A component will be fixed in order to apply to camt.077 CUMU the rounding foreseen by UDFS. 7. CRDM object: na 8. DWH report: na | BILL | 2025-02-15
PBI000000230211 | T2 | 1. Business Scenario Description: users trying to configure a new AAU for accounts linked to Contingency Accounts or trying to create new Contingency Accounts. 2. Issue Description: As stated in the ECONS II UDFS 1.3.2.5. Reference data for accounts in ECONS II û ôEach Authorised Account User can be linked to one and only one Contingency Accountö but on CRDM side no Business Rule prevents the creation of multiple Authorised Account Users with different AAU BICs for accounts which are linked to Contingency Accounts. 3. Workaround: no workaround available. Customers need to make sure that only one AAU is defined for accounts which are linked to Contingency accounts. 4. TARGET Services concerned: T2, T2S, TIPS 5. Effects and restrictions on concerned TARGET Service: no usage restriction. 6. Required SW change: During AAU creation, update and restore operations, CLM Accounts, System needs to check that CLM CB Accounts and Ancillary System Technical Accounts, if already linked to Contingency Accounts, cannot have multiple AAUs with different BICs for overlapping validity periods. During Contingency Accounts creation, update and restore operations, Linked Account needs to be checked to make sure that it has only one Authorised Account User during cash account validity period. 7. CRDM object:Authorised Account User, Cash Account | CRDM | 2025-06-14
PBI000000230942 | T2 | 1. Business Scenario Description: RTGS Directory is based on Authorised Account User and Cash Account configuration. To exclude a BIC from the directory, it should be referenceed in an AAU linked to a non published cash account or in an Exclusion participation type AAU, also within a wild card pattern. A BIC should be included only once within the same validity period in order to uniquely identify the correct addressing. 2. Issue Description: A BIC has been defined as Direct AAU on a non published account. The same BIC is included in a wild card pattern for a multi addressee AAU created on a published account. Expected behaviour should be that the BIC should not be part of the RTGS Directory. Currently the software wrongly includes the BIC when evaluating the wild card pattern instead of skipping it. The result is that a wrong record for the BIC is produced in the directory, causing as a side effect a double entry for the BIC with overlapping period. The fix aims at correcting the wild card pattern evaluation routine so that the processing is in line with the specs. 3. Workaround: In such scenario, if an additional AAU is created for the BIC on the published account with participation type set to "Exclusion", the record would not be included in the directory as expected. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: RTGS directory is used only in the context of RTGS and distributed to the RTGS participants, there is no impact on other services. 6. Required SW change: Yes. The wild card evaluation routine for the RTGS Directory extraction component should be corrected 7. CRDM object: RTGS Directory 8. DWH report: N/A | CRDM | 2025-06-14
PBI000000231653 | T2 | 1. Business Scenario Description: users trying to configure a new AAU for accounts linked to Contingency Accounts or trying to create new Contingency Accounts. 2. Issue Description: As stated in the ECONS II UDFS 1.3.2.5. Reference data for accounts in ECONS II û ôEach Authorised Account User can be linked to one and only one Contingency Accountö but on CRDM side no Business Rule prevents the creation of multiple Authorised Account Users with different AAU BICs for accounts which are linked to Contingency Accounts. 3. Workaround: no workaround available. Customers need to make sure that only one AAU is defined for accounts which are linked to Contingency accounts. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: no usage restriction. 6. Required SW change: During AAU creation, update and restore operations, CLM Accounts, System needs to check that CLM CB Accounts and Ancillary System Technical Accounts, if already linked to Contingency Accounts, cannot have multiple AAUs with different BICs for overlapping validity periods. During Contingency Accounts creation, update and restore operations, Linked Account needs to be checked to make sure that it has only one Authorised Account User during cash account validity period. 7. CRDM object: Authorised Account User, Cash Account | CRDM | 14/06/2025
PBI000000232168 | T2 | 1.Business Scenario: A duly authorized CRDM U2A user modifies the "System User Reference" field of a User falling under data scope. The modified user is employed by a party to access the ECONS2 module via U2A. 2. Issue Description: Due to a software bug, the user with a modified "System User Reference" cannot access the ECONS2 module via U2A until the next data propagation event. 3. Workaround: no workaround available. 4. TARGET Services concerned: ECONS2 5. Effects and restrictions on concerned TARGET Service: this only impacts the ECONS GUI. 6. Required software change: fix the software bug in order not to block the access to the ECONS GUI for the period between the modification of the "System User Reference" and the next data propagation. 7. CRDM object: User 8. DWH Report: N/A | CRDM | 2025-06-14
PBI000000232441 | T2 | 1. Business Scenario Description: RTGS directory is built from the Authorised Account User and includes BIC11 entries out of the possible wild cards defined for the AAUs. Deletion records should be included in the directory either if an AAU is closed for the upcoming business date and if a BIC is closed. 2. Issue Description: When a BIC is closed but there is a wildcard Authorised Account User including that BIC, a deletion record is not sent in the related directory. 3. Workaround: no workaround 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Directories on customer side out of date compared to actual active BICs. 6. Required SW change: The BIC Valid To date shall be considered when deletion records are processed 7. CRDM object: RTGS Directory, CLM Repository 8. DWH report: n/a | CRDM | 2025-06-14
PBI000000233623 | T2 | 1. Business Scenario Description: When performing a Liquidity Transfer Order update request in A2A, in case the Valid From is not specified in camt.024, the business rule DCU4073 is erroneously triggered. 2. Issue Description: Due to a software bug, Standing/Predefined LTO cannot be updated via A2A when Valid From field is not specified. 3. Workaround: Specify the Valid From field whenever updating the LTO via A2A or use the U2A channel to update the very same LTO. 4. TARGET Services concerned: T2, T2S. 5. Effects and restrictions on concerned TARGET Service: Standing/Predefined LTO cannot be updated via A2A when Valid From field is not specified. 6. Required SW change: Fix the software behavior of the business rule DCU4073 in order to handle the cases when the ôValid Fromö field is not specified in the input A2A request. 7. CRDM object: Liquidity Transfer Order. 8. DWH report: n/a | CRDM | Awaiting FA
PBI000000233356 | T2 | 1. Business Scenario Description:A duly authorised CRDM U2A user attempts to create/update a CLM party-service link (PSL) defining the minor entity CLM configuration data. Specifically, it defines the the field "Maximum amount for overnight deposit" specifying a value comprising a decimal part (mantissa). 2. Issue Description: The problem depends on the fact that for the field "Maximum amount for overnight deposit", the decimal values are not currently handled by the CRDM GUI and BE side. Indeed, the correct behaviour is that the number decimal values of the "Maximum amount for overnight deposit" depends on the currency of the system entity. For example for the currency EUR there should be 2 decimals (cents). 3. Workaround: N/A 4. TARGET Services concerned: T2 (CLM) 5. Effects and restrictions on concerned TARGET Service: A user is not able to create/update a PSL defining the field "Maximum amount for overnight deposit" with the decimal part (mantissa) defined. 6. Required SW change: Add a new business rule to properly handle the correct field format the field "Maximum amount for overnight deposit", i.e., to check that it is compliant to the system entity currency. 7. CRDM object: Party-Service Link. 8. DWH report: N/A | CRDM | 2025-06-14
PBI000000234575 | T2 | 1. Business Scenario Description: A duly authorised CRDM User attempts to close a cash account referenced in a deleted Data Aggregation (e.g., Account Monitoring Group, Liquidity Transfer Group, Settlement Bank Account Group) causing the business rule DCU1030 to be wrongly triggered. 2. Issue Description: The current business rule check on the account linked in a Data Aggregation entity does not make a distinction between active and deleted groups. 3. Workaround: no workaround is feasible 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: if the cash account is referenced in a deleted data aggregation, it is not possible to close the account. 6. Required SW change: update of the processing of error DCU1030 in order to consider only the active data aggregation objects. 7. CRDM object: Data Aggregation (Account Monitoring Group, Liquidity Transfer Group, Settlement Bank Account Group) 8. DWH report: N/A | CRDM | 2025-11-22
PBI000000234545 | T2 | 1. Business Scenario Description:When the base Authorised Account User is closed, a deletion RTGS Directory record is included both in the full and update versions of the directory. 2. Issue Description: The deletion record for the scenario should be included in the directory produced for the Valid To + 1 business day. Currently it is included in the version valid for the Valid To date 3. Workaround: No workaround is available 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Customer application processing the directories could create wrong addressing for those records. 6. Required SW change: The RTGS DIrectory processing component needs to be fixed and consider the Valid To + 1 date when creating deletion records 7. CRDM object: RTGS Directory processing component 8. DWH report: | CRDM | 2025-06-14
PBI000000234605 | T2 | 1. Business Scenario Description: Wildcards authorised account users have been setup referencing the related RTGS Account. Some of the BICs included in the wildcard had been referenced in other Authorised Account User for a different TARGET Service. Those BICs have not been included in the RTGS Di-rectory. 2. Issue Description: Because of a failing algorithm, if the same BIC has been defined inside a wildcard for RTGS addressing and at the same time as authorised BIC for another TARGET Service (e.g. TIPS), the extraction of data resulted in the exclusion for these records. 3. Workaround: No Workaround available 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: A wrong RTGS directory content could lead to payment addressing issues for the partici-pants, reducing the reachability of impacted financial institutions. 6. Required SW change: Roll-back of the PBI causing the issue (hotfix), fixing of the data extraction logic in order to take account only authorised account users entry for the RTGS service. 7. CRDM object: - 8. DWH report: - | CRDM | 2025-11-22
PBI000000234566 | T2 | 1. Business Scenario Description: A duly authorised CRDM U2A user searches for liquidity transfer orders in the Standing/Predefined Liquidity Transfer Orders Search screen. Then, the very same user attempts to download the result list of the liquidity transfer orders. 2. Issue Description: when the "Amount From" specified in the search criteria of the mentioned screen is greater than 21,474,836, due to a software bug, it is not possible to download the result list of liquidity transfer orders. Some unexpected errors are raised in the GUI, namely, "Unable to Download Liquidity Transfer Orders" and "Unable to download Standing/Predefined Liquidity Transfer Orders". 3. Workaround: to download the very same set of objects, it is possible to remove the filter in the search criteria and apply it afterwards on the result list. 4. TARGET Services concerned: T2, T2S 5. Effects and restrictions on concerned TARGET Service: a CRDM U2A user is unable to export the liquidity transfer orders list. 6. Required SW change: fix the bug to allow users to export the liquidity transfer orders whenever any filter is applied on the "Amount From" field as a search criteria. 7. CRDM object: Liquidity Transfer Order 8. DWH report: N/A | CRDM | 2025-06-14
PBI000000232289 | T2 | 1. Business Scenario Description: Receiving A2A messages sent by the DWH 2. Issue Description: The field<DWHRptID> is useless in its current form and should be functionally converted to support the file splitting function 3. Workaround: None 4. TARGET Services concerned: T2-DWH 5. Effects and restrictions on concerned TARGET Service: The field is useless in its current form as it is not filled uniquely 6. Required SW change: Since the content of the field <DWHRptID> is deemed useless this field should contain a page number (in total in format '02/03" (meaning page 2 of 3)). This shall be applied together with the file split functionality which will make it possible, that also reports exceeding the 90MB file size limit can be sent via A2A as described in the DWH UDFS. In order for the receiver to know, how many pages he has to expect and in what order they need to be put together again, this information is indispensable. 7. CRDM object: - 8. DWH report: All | DWH | 2025-06-14
PBI000000232349 | T2 | 1. Business Scenario Description: Usage of T2-DWH PDR IDC03 2. Issue Description: Report can no longer display data that is prior to a CRDM change to the customer's account 3. Workaround: None 4. TARGET Services concerned: T2-DWH 5. Effects and restrictions on concerned TARGET Service: Changes to the customer's account can lead to new entries in a DWH table used by the report. As a result, only the most recent entry is listed as "Active". The report then uses the "Valid From" date of the "Active" entry as the earliest possible date to retrieve and display data. 6. Required SW change: Adjustment to the ETL process and the filtering of the report so that the report can also display entries without an "Active" flag 7. CRDM object: - 8. DWH report: IDC03 | DWH | 2025-06-14
PBI000000233529 | T2 | 1. Business Scenario Description: Usage of T2-DWH PDR IDH05 (Historical CRSS Data) 2. Issue Description: Some accounts are missing compared to previous CRSS reports 3. Workaround: None 4. TARGET Services concerned: T2-DWH (PROD only, as the CRSS data is only available there) 5. Effects and restrictions on concerned TARGET Service: Due to dependencies in the historical static data, it is possible that the objects have not been assigned to the corresponding data scope and therefore cannot be called up 6. Required SW change: Adjustment and extension of the historical static data, as well as a reload and/or adjustment of the corresponding data tables in order to be able to carry out a correct allocation 7. CRDM object: - 8. DWH report: IDH05 / CRSS Data Objects | DWH | 2025-06-14
PBI000000233848 | T2 | 1. Business Scenario Description: Usage of DWH Data Object "Parties - Cash Accounts - Other Info.Cash Accounts Private Data" in User Defined Report. 2. Issue Description: Missing columns regarding Co-Management and MR Inclusion in elements of data object. 3. Workaround: None 4. TARGET Services concerned: T2 DWH 5. Effects and restrictions on concerned TARGET Service: Usage of DWH data object is restricted due to missing data 6. Required SW change: The ETL job for the source table of "Cash Accounts Private Data" needs to be redesigned. After deployment of this change, a purge and a complete reload of this table is mandatory on all stages. 7. CRDM object: n.a. 8. DWH report: ANS01, IDC01, IDC02, IDC03, IDC04, IDC05 | DWH | 22/11/2025
PBI000000234015 | T2 | 1. Business Scenario Description: Usage of T2-DWH PDR PAR02 2. Issue Description: DWH Report PAR02 shows an excessive number of participants 3. Workaround: None 4. TARGET Services concerned: T2-DWH 5. Effects and restrictions on concerned TARGET Service: Due to an incorrect aggregation, the number of participants displayed in the report is too high. This exceeds the number of entries. 6. Required SW change: Adjustment of the counting function so that the number in the report matches the entries in the report and CRDM 7. CRDM object: - 8. DWH report: PAR02 | DWH | 2025-06-14
PBI000000234049 | T2 | 1. Business Scenario Description: Usage of T2-DWH & T2S-DWH PDR 2. Issue Description: The Tab Issue defines that only the first tab of the HTML version is exported when using Excel Data, CSV and XML 3. Workaround: Advanced users can schedule every tab as UDR in most cases 4. TARGET Services concerned: T2-DWH & T2S-DWH 5. Effects and restrictions on concerned TARGET Service: Some of the existing PDRs are divided into several tabs to make them easier for users to understand. These tabs are displayed correctly in formats that are optimized for U2A use (HTML, PDF and Excel). However, formats that are optimized for A2A processing (Excel Data, CSV and XML) are only exported with the first tab due to a COGNOS setting that cannot be changed. 6. Required SW change: Extension of the prompt page to include a query as to which page is intended for export in Excel Data, CSV and XML formats. This can also be used for scheduling. 7. CRDM object: - 8. DWH report: All DWH PDR with more than one tab T2: BDY01, BIL01*, BIL02, BIL03*, CON01, IDC02, MIR01, PAR01, PAR02, PAR03, TRN05, TRN07, TRN08. TRN09*, TRN10, TRN11* T2S: INX01, RAL01, SCT03 PDRs marked with * also contain the data issue (PBI000000234051), which must be considered separately | DWH | 22/11/2025
PBI000000234051 | T2 | 1. Business Scenario Description: Usage of T2-DWH & T2S-DWH PDR 2. Issue Description: The Data Issue defines that only the first list / report objects are reflected when using Excel Data, CSV and XML (in consequence not all data are displayed) 3. Workaround: Workaround via Excel (manual conversion into csv for example) 4. TARGET Services concerned: T2-DWH & T2S-DWH 5. Effects and restrictions on concerned TARGET Service: Some of the existing PDRs are divided into several tables to make them easier for users to understand. These tables are displayed correctly in formats that are optimized for U2A use (HTML, PDF and Excel). However, formats that are optimized for A2A processing (Excel Data, CSV and XML) are only exported with the first table due to the fact the machine-readable formats require a uniform table structure. 6. Required SW change: Output of the data as raw data without the respective formations in order to achieve a uniform table structure. 7. CRDM object: - 8. DWH report: All DWH PDR with more than one table T2: ANS02, BIL01*, BIL03*, INV01, TRN03, TRN04, TRN06, TRN09*, TRN11* T2S: RES01, RES02, SCT04, SST01, SST02, SST03 PDRs marked with * also contain the tab issue (PBI000000234049), which must be considered separately | DWH | 22/11/2025
PBI000000234411 | T2 | 1. Business Scenario Description: Usage of predefined report MIR01 2. Issue Description: No data found on tab 2 (interest rates) in case user selected one or more parties on the prompt page 3. Workaround: Do not use the party filter 4. TARGET Services concerned: T2 DWH 5. Effects and restrictions on concerned TARGET Service: The MIR01 report does not work as specified in the special case a party filter is used 6. Required SW change: For the MIR01 report the implementation of the party filter in Cognos has to be modified to use the DWH internal party technical identifier (Party_SK) instead of the Party_BIC. 7. CRDM object: - 8. DWH report: MIR01 | DWH | 2025-06-14
PBI000000234132 | T2S | 1. Business Scenario Description: CRDM User trying to create a Party. 2. Issue Description: when a CB User is trying to create a National Central Bank Party, the operation is rejected with an unknown technical error instead of a classic Business Rule. 3. Workaround: not present and not needed, this business case is not foreseen for customers. 4. TARGET Services concerned: T2, T2S, TIPS. 5. Effects and restrictions on concerned TARGET Service: no restrictions. 6. Required SW change: software fix in order to display the correct triggered Business Rule, instead of the technical error. 7. CRDM object: Party. 8. DWH report: n/a. | CRDM | 2025-06-14
PBI000000234166 | T2S | 1. Business Scenario Description: A user clicks on CMB details button of the Limit Search/List screen. 2. Issue Description: Due to an issue in the update of the CMB details button status of the Limit Search/List screen, when selecting a T2 multilateral limit the ôCMB detailsö button is wrongly enabled; additionally, after clicking on this button it is displayed the CMB details screen related to a limit different from the previous selected. 3. Workaround: No workaround. 4. TARGET Services concerned: T2, T2S, TIPS. 5. Effects and restrictions on concerned TARGET Service: No effects and restrictions since it is just a visualization issue. 6. Required SW change: The SW change will fix an issue in the update of the CMB details button status of the Limit Search/List screen. 7. CRDM object: Limit. 8. DWH report: N/A. | CRDM | 2025-06-14
PBI000000234204 | T2S | 1. Business Scenario Description: BILL user trying to print the .pdf file of the Itemised Invoice Data Details screen for download purposes, using the related on-screen button. 2. Issue Description: After hitting the button, the GUI does not produce any .pdf file. 3. Workaround: Exporting the screen content in .xls with the export button. 4. TARGET Services concerned: T2, T2S, TIPS. 5. Effects and restrictions on concerned TARGET Service: minor restriction on .pdf exporting. 6. Required SW change: GUI fix in order to correctly produce the .pdf file of the webpage after hitting the button. 7. CRDM object: n/a. 8. DWH report: n/a. | BILL | 2025-06-14
PBI000000234361 | T2S | 1. Business Scenario Description: CRDM User displaying the details of an existing Message Subscription Rule Set (and the whole set of its rules) via the dedicated Message Subscription Rule Set Details GUI screen. 2. Issue Description: Due to some wrong filtering conditions, the GUI is not able to display Message Subscription Rules having 0 predicates. 3. Workaround: no workaround feasible. 4. TARGET Services concerned: T2, T2S, TIPS. 5. Effects and restrictions on concerned TARGET Service: no restrictions since empty rules have no effects in the system. 6. Required SW change: CRDM GUI filtering fix in order to display all the rules, unconditionally. 7. CRDM object: Message Subscription Rule. 8. DWH report: n/a. | CRDM | 2025-06-14